## Dashboard
DeepRank SEO Agent — Progress Tracker
Generated 2026-09-12 from seo-agent/tasks
| Done | Total | Share
Completed task packages (T1–T19) | 15 | 22 | 68%
Day tracks completed | 2 | 5 | 40%
Deliverable checkboxes marked | 120 | 181 | 66%
Remaining task packages (Day 3 balance) | 7 | 22 | 32%
Phase completion
P1 — Scaffold + Config (Day 1) | 100% | Foundation: package, config service
P2 — Database (Day 1) | 100% | Schema, migrate, seed, 5 keywords + 5 pages
P3 — Deterministic Tools + Driver wiring (Day 2) | 100% | SERP mock, GSC stub, crawl, build, validate
P4 — LLM Brain (Day 3, in progress) | 100% of P4 code (T12–T14) done; T19 reviewer hardening done too | prompts, Groq brain, Driver wire, reviewer probes all green against real key
P5 — PR + Measure (Day 3, not started) | 0% | T15, T16, T17, T18, T20, T21, T22: github.ts, measure, real swaps, workflows
P6 — Live run + Runbook + hardening (Day 4–5) | 0% | E2E, runbook.md, monitoring
Key stats
Completed task packages | T1–T19 (15 of 22) — P1–P3 + P4 (prompts, Groq brain, Driver wire, reviewer hardening)
Verification evidence | dry-run exit 0 with real Groq key; reviewer probes 4/4 green (fabrication/scope/positioning→fail, clean→pass); winner 32,800 (spec Example A)
Remaining task packages | T15 (github.ts), T16 (wire github), T17 (SERP swap), T18 (GSC swap pending), T20 (measure), T21 (GH Actions), T22 (cli wiring)
Next milestone | T15 — github.ts (branch/commit/draft PR via Octokit); T17 — SerpApi real swap (signed up), GSC creds still pending
Overall delivery | P1–P4 code complete = ~75% toward a live closed-loop agent (Day 1–3 of 5)

## Task Log (Done T1–T19)
Completed tasks — T1 to T19
Imported and verified from day-1.md, day-2.md, day-3.md
Day | Task | Phase | Title | Importance | Status | Verification evidence / Notes
Day 1 | T1 | P1 | Package scaffold (bun, tsconfig, .env, standalone package) | Critical | DONE | tsc clean; scaffold boots; pg wrapped in Effect (dropped @effect/sql-pg beta skew)
Day 1 | T2 | P1 | Config service (typed env, fail-fast) | Critical | DONE | missing key names itself; redacted secrets
Day 1 | T3 | P2 | Database service + schema (5 tables) + seed | High | DONE | postgres:16-alpine; idempotent migrate+seed; volume/difficulty NULL (no fabrication)
Day 1 | T4 | P2 | XState v5 machine + Driver | Critical | DONE | REVISE ≤3 retries then ABORT
Day 1 | T5 | P2 | Tools registry (6 contracts via Effect Schema) | High | DONE | contracts decode sample payloads
Day 2 | T6 | P3 | SERP tool (mock) | High | DONE | 5 keywords x 10 .example results
Day 2 | T7 | P3 | GSC tool (stub) | High | DONE | clicks/impressions/pos/ctr + 28d trend
Day 2 | T8 | P3 | Crawl tool (real) | High | DONE | live fetch + node-html-parser, broken-link check
Day 2 | T9 | P3 | Build tool (real astro build gate) | Critical | DONE | ok on repo; failing fixture -> 2 parsed errors
Day 2 | T10 | P3 | Validate tool (real) | Critical | DONE | title/desc/JSON-LD specs enforced
Day 2 | T11 | P3 | Wire tools into Driver | Critical | DONE | winner amazon seller gst accounting = 32,800
Day 3 | T12 | P4 | Prompts.ts (driver, revise, reviewer) with spec constraints | High | DONE | POSITIONING_RULES + METADATA_RULES embedded
Day 3 | T13 | P4 | Brain.ts — Groq LLM service via raw fetch | High | DONE | JSON mode; stub fallback without key; works with real key
Day 3 | T14 | P4 | Wire Brain into Driver (PLAN/ACT/REVISE/REVIEWER) | Critical | DONE | full loop exit 0 (real LLM key)
Day 3 | T19 | P4 | Reviewer hardening — 4 fixture probes | High | DONE | review -> {verdict, reason}; 4/4 green: fabrication/scope/positioning fail, clean pass; REAL Groq key

## Remaining Work
Remaining work — Day 3 balance (T15–T22)
T12–T14 + T19 done; SERP=SerpApi signed up; GSC creds PENDING
Day | Task | Phase | Title | Importance | Status | What it unblocks
Day 3 | T15 | P5 | github.ts — branch, commit, draft PR via Octokit | Critical | NOT STARTED | CREATE_PR stub -> real PR; needs GITHUB_TOKEN (placeholder in .env)
Day 3 | T16 | P5 | Wire github.ts into Driver (replace CREATE_PR stub) | Critical | NOT STARTED | real branch + commit + draft PR + db updates
Day 3 | T17 | P5 | Real SERP swap — SerpApi (signed up) | Medium | NOT STARTED | SERPAPI_KEY in .env; mock fallback when absent
Day 3 | T18 | P5 | Real GSC swap — Search Console API (PENDING) | Medium | NOT STARTED | GSC creds not granted yet; stub + documented TODO swap path
Day 3 | T20 | P5 | measure.ts — DETECT_MERGES → GSC_PULL → WRITE_DELTAS → LEARNINGS → FEED_RESEARCH | High | NOT STARTED | loop-back so agent learns
Day 3 | T21 | P5 | GitHub Actions — optimize.yml (weekly) + measure.yml (monthly) | High | NOT STARTED | scheduled runs + workflow_dispatch
Day 3 | T22 | P5 | cli.ts wiring — stack all Live layers + measure command | High | NOT STARTED | CLI runs full real pipeline end-to-end
Day 4 | — | P6 | E2E test + runbook.md + error handling + first live run | High | NOT STARTED | production-ready closed loop
Day 5 | — | P6 | Monitoring + tuning + buffer | Medium | NOT STARTED | calibrated production behavior

## Importance Map
Why each piece matters — importance ratings
Priority drives build order.
Item | Importance | Why it matters (impact if missing)
Config service (T2) | Critical | typed env, fail-fast at boot
Database + schema (T3) | Critical | single source of truth
State machine (T4) | Critical | orchestration + REVISE cap
Build gate (T9) | Critical | no PR without green astro build
Validate gate (T10) | Critical | metadata specs enforced in code
Driver wiring (T11) | Critical | proves P3 works
Prompts (T12) ✓ | High | positions DeepEcom, bans fabrication
Groq brain (T13) ✓ | High | LLM service; stub fallback
LLM → Driver wire (T14) ✓ | Critical | intelligent PLAN/ACT/REVISE/REVIEWER
Reviewer hardening (T19) ✓ | High | deterministic guard; 4/4 probes green
Real PR — github.ts (T15) | High | closed loop — nothing ships without it
Measure job (T20) | High | agent can't learn without loop-back
GSC/SERP real swaps (T17–T18) | Medium | stub data plausible; real is accurate
GH Actions + cli wiring (T21–T22) | Medium | hands-off scheduled runs